## CRM_main
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch | Welded | Critical Information
New Swindon College | SO-1736 | PO0189522-1 | Fins & Subframe Prod. 2 | In production |  | SN2 1DY | Tetraclad Ltd New Swindon College North Star Avenue Swindon, SN2 1DY | 2025-06-03 | 2025-09-16 | 0.3333% | 1% | 0% | 0% | Yes | Riggid Lorry + Trailer Heavy Load
Panoramic | SO-1850 | PAN216 | Additional Panels | Ready to Dispatch |  | NW3 2QX | FC Direct Ltd, CO GPF Lewis, 152 Fleet Road, London, NW3 2QX Luis Valle +44 (0) 7765 777 672, Shaun Holland +44 (0) 7846 211 254, Aaran Barratt +44 (0) 7464 485 453 | 2025-08-06 |  | 83.33% | 100% | 100% | 50%
Briggate Leeds | SO-1853 | P6241090 | Flashings | In production |  | LS1 6DE | HG Construction Limited Store House Briggate 140-142 Briggate Lane Rear of House of Fraser, Access via Central Road (Opposite Little Tokyo Restaurant) Leeds, LS1 6DE Ion +44 (0) 7843 117 869 | 2025-08-08 |  | 0.3333% | 1% | 0% | 0%
William Street | SO-1863 | WLMS035 | Replacment Panels & Pressings | In production |  |  | Powdertech (Corby) Ltd 5 Cockerell Rd Corby NN17 5DU Contact: Richard +44 (0) 7977 260 382 | 2025-08-19 |  | 0.3333% | 1% | 0% | 0%
Maiden Lane | SO-1869 | EBS001 | Cabinet Prod.2 | In production |  |  | EK Construction Limited 143 Ebury Street London SW1W 9QN | 2025-08-21 |  | 0.3333% | 1% | 0% | 0% | Yes
CGY | SO-1870 | 2126 | Block B Remaining Cills | In production |  | NW1 8EH | St George Plc Camden Goods Yard Chalk Farm Road, Chalk Farm Camden Town,London, NW1 8EH Kontakt: Arek +44 (0) 7534 515 939 | 2025-08-22 | 2025-09-16 | 18.67% | 56% | 0% | 0% | Yes | Riggid Lorry + Trailer Heavy Load
CGY | SO-1875 | 2136 | CW Brackets | In production |  | NW1 8EH | St George Plc Camden Goods Yard Chalk Farm Road, Chalk Farm Camden Town,London, NW1 8EH Kontakt: Arek +44 (0) 7534 515 939 | 2025-08-27 | 2025-09-16 | 14.67% | 44% | 0% | 0% | Yes | Riggid Lorry + Trailer Heavy Load
CGY | SO-1875 | 2137 | CW Reinforcments | In production |  | NW1 8EH | Vidok Sp. Z.o.o. 36-054 Mrowla Rudna Mala 75 | 2025-08-27 |  | 0.3333% | 1% | 0% | 0% | Yes
Wembley | SO-1876 | 2147 | Flashings | In production |  | HA9 0GB | FCS Facades, McAleer & Rushe Contracts UK, 10 Fulton Road, Wembley, London, HA9 0GB | 2025-09-02 |  | 0.3333% | 1% | 0% | 0%
Kings Road Park E2 | SO-1877 | PO13424-439-JB-KRP | Perforated Balustrades | In production |  | 84 – 300 | A-Lakiernia Sp. z o.o. ul. Krzywoustego 1, 84 – 300 Lębork | 2025-09-02 |  | 0.3333% | 1% | 0% | 0% | Yes
Drury Lane | SO-1879 | 2151 | Rooflight Pressings | In production |  | WC2B 5PN | McAleer & Rushe Contracts UK Ltd (For FCS Facades) 161 Drury Lane London, WC2B 5PN Contact: Ruslan +44 (0) 7896 059 740 | 2025-09-02 |  | 0.3333% | 1% | 0% | 0%
King Street | SO-1880 | M-CC1084/00071 | Flashings | In production |  | WC2E 8HN | 26 King Street, London, WC2E 8HN Contact: +44 (0) 7540 994 243 | 2025-09-05 |  | 0.3333% | 1% | 0% | 0% | Yes
Firestone | SO-1881 | M-CC1093/00087 | Panels | In production |  | TW8 9EP | West Cross Industrial Park, Brendford, TW8 9EP Contact: Paul Yates - +44 (0) 7879 882133 | 2025-09-05 |  | 0.3333% | 1% | 0% | 0% | Yes
Kings Road Park E2 (Stavley Road) | SO-1882 | PO30625-458-SRP | Flashings | In production |  | W4 3HU | 76 Stavley Road, W4 3HU London | 2025-09-05 |  | 0.3333% | 1% | 0% | 0% | Yes
Bromley | SO-1883 | 37-61JA | L-Profiles | In production |  | BR2 9AP | Roytec Ltd c/o RED ,Construction Group , 5 Simpsons Road, St Marks Square, London Bromley BR2 9AP Contact: Oleg +447453009655 , Andriy +447380330922 . Nick +07447162592 | 2025-09-08 |  | 0.3333% | 1% | 0% | 0%
BDF Showroom | SO-1884 | Pang - 9765 | Helena Pang Door Skins | In production |  | UB7 7HQ | Bifold Door Factory Ltd. Bingley The Common West Drayton UB7 7HQ | 2025-09-08 |  | 0.3333% | 1% | 0% | 0% | Yes
Broadway Central 2 | SO-1885 | 2183 | Panel Hooking System | In production |  | G2 3BW | McAleer & Rushe Contracts UK Ltd (For FCS Facades) ,Broadway Central PBSA, Renfield Street Glasgow, G2 3BW Contact: Piotr +44 (0) 7471 273 458 | 2025-09-09 |  | 0.3333% | 1% | 0% | 0%
Slough CDC | SO-1886 | PO00443 | Copings | In production |  | SL1 2BJ | Upton Hospital (CDC) , Church Street, SLough, SL1 2BJ Alfie Kelmendi +44 (0) 7908 701565 | 2025-09-10 |  | 0.3333% | 1% | 0% | 0% | Yes
CGY | SO-1887 | 2190 | Spandrel, Arched & Urban Entrance Panels | In production |  | NW1 8EH | St George Plc Camden Goods Yard Chalk Farm Road, Chalk Farm Camden Town,London, NW1 8EH Kontakt: Arek +44 (0) 7534 515 939 | 2025-09-10 |  | 0.3333% | 1% | 0% | 0%

## VRP
Drummond Street | SO-1816 | PO02502 | Curved Flashings | In production | NW12PB | 155 Drummond Street London Camden NW12PB Pawel +44 (0) 7590 056 393 | 2025-07-15 | 0.3333% | 1% | 0% | 0% | Yes

## Aurora
Plumstead West Thamesmead | SO-1766 | PO4503 | In production | SE28 0FA | Berkeley Homes Building Site Gate 3 Manor Ground Hadden Road Plumstead SE28 0FA Contact: +44 (0) 7830 377 888 | 0.3333% | 1% | 0% | 0%

## Roytec
Bromley | SO-1716 | 37-27JA | Flashings | In production | BR2 9AP | Roytec Ltd c/o RED Construction Group 5 Simpsons Road St. Marks Square BR2 9AP, London Oleg +44 (0) 7453 009 655 Andriy +44 (0) 7380 330 922 Nick +44 (0) 7447 162 592 | 0.3333% | 1% | 0% | 0%
[5 empty] | SE9 5DA | Roytec 27 Passey Place London SE9 5DA Nick +44 (0) 7447 162 592 Jurij +44 (0) 7888 504 050
[5 empty] | EC2A 3AR | Roytec LTD c/o RED Construction 134-146 Curtain Rd London EC2A 3AR Nick +44 (0) 7447 162 592 Jurij +44 (0) 7888 504 050

## FC Direct
The Panoramic | SO-1707 | PAN148 | Cassette Panels | In production | DA1 4QN | FC Direct Ltd. 1 Kennet Road Dartford Kent, DA1 4QN | 2025-05-14 | 0.3333% | 1% | 0% | 0%

## Tanner Homes
T

## Craft Interior Limited
Sarawak adn Dayak | SO-1577 | 1178-042 AR 1178-043 AR | Sub-Frame and Panel | In production | SE15 3SS | Craft Interior Ltd C/O Equans Dayak Court 71 Consort rd (access via Brayards rd) London, SE15 3SS | 2025-02-26 | 0.3333% | 1% | 0% | 0%

## Fleetwood
Union Square | SO-1509 | P27547S P27548S P27549S | Brackets | In production | NE2 1BS | C/O Fleetwood Architectural Aluminium Union Square Stoddart Street Shieldfield NE2 1BS | 2025-01-16 | 0.3333% | 1% | 0% | 0%

## Roswick
Tablot Mill | SO-1453 | ROS404/28244 | Windows Z-Brackets | Galvanized | M15 4JY | CR Construction Limited Talbot Mill Ellesmere Street M15 4JY, Manchester | 2024-11-05 | 2024-11-12 | 39.5% | 79% | 0%

## Marco
IQ Aldgate | SO-1447 | PO0167996-1 | Soffit Panels Prod. 2 | In Production | ME10 1WZ | Marco Industries A Trading Division Of Vink UK Ltd Units 1-2 152 Staplehurst Road Sittingbourne, ME10 1WZ | 2024-10-29 |  | 0.3333% | 1% | 0% | 0%
IQ Aldgate | SO-1447 | PO0167996-1 | Soffit Panels Prod. 2 | Ready to Dispatch | ME10 1WZ | Marco Industries A Trading Division Of Vink UK Ltd Units 1-2 152 Staplehurst Road Sittingbourne, ME10 1WZ | 2024-10-29 | 2024-11-11 | 83.33% | 100% | 100% | 50%
Woodlands Chase | SO-1502 | PO0173636-3 | Flashings | Ready to Dispatch | PO15 7FG | C/O New Build Carpentry Taylor Wimpey Woodlands Chase Phase 3a Whiteley Meadows Ridge Farm Botley FAREHAM, PO15 7FG
The Height |  |  |  |  | SE7 8JJ | SD Plastering The Heights Charlton SE7 8JJ
New College Swindon |  |  |  |  | SN2 1DY | Tetraclad Ltd New Swindon College North Star Avenue Swindon, SN2 1DY
Woodlands Chase | SO-1654 | PO0183916-1 | Flashings | Ready to Dispatch | PO15 7FG | C/O New Build Carpentry Taylor Wimpey Woodlands Chase Phase 3a Phase 3a, Woodlands Chase North Whiteley SOUTHAMPTON, SO30 2YT Kontakt: Matt +44 (f0)7470 111504
Barrets Grove |  |  |  |  | N16 8AP | Tetraclad 91 Barrets Grove Stoke Newington LONDON, N16 8AP
Woodlands Chase |  |  |  |  | SO30 2YT | C/O New Build Carpentry Taylor Wimpey Woodlands Chase Phase 3a Phase 3a, Woodlands Chase North Whiteley SOUTHAMPTON, SO30 2YT
Centrium CT2 |  |  |  |  | AL1 2RE | Tetraclad Ltd Wilshere Avenue ST ALBANS, AL1 2RE Ross Bridger +44 (0) 7850985167
Cherry Orchard |  |  |  |  | CR0 4BG | Formation Design & Build Ltd Stafford Road CROYDON, CR0 4BG United Kingdom Daniel +44 (0) 7369 217 437
Ebbsfleet |  |  |  |  | DA10 0BE | Tetraclad Ltd, EBBSFLEET GREEN, Site A - Ackers Drive, Ebbsfleet Valley, Kent, DA10 0BE, Contact: +44 (0) 7850 985 167

## Bifold Door
BDF Showroom | SO-1435 | BDFA0035 | C-Channel Pressings | In production | UB7 7HQ | Bifold Door Factory Ltd. Bingley The Common West Drayton UB7 7HQ | 2024-10-16 |  | 0.3333% | 1% | 0% | 0%
BDF Showroom | SO-1441 | BDFMO-359 | Cills | Ready to Dispatch | UB7 7HQ | Bifold Door Factory Ltd. Bingley The Common West Drayton UB7 7HQ | 2024-10-21 | 2024-11-11 | 83.33% | 100% | 100% | 50%

## Kladworx
Greenwich High Rd | SO1423 | PO00345 | Copings | In Production | SE10 8JL | Kladworx Ltd 27 Greenwich High Rd London SE10 8JL | 2024-10-08 | 0.3333% | 1% | 0% | 0%
Genome Campus | SO-1459 | PO00365 | Cladding Panels & Portal | In Production | CB10 1SA | Beardwell Construction (Site) Kladworx Ltd Wilcome Genome Campus Thornton Connectivity CB10 1SA | 2024-11-12 | 0.3333% | 1% | 0% | 0%
Lyndhurst Road | SO-1578 | PO00400 | Sub-Frame | In Production | BN11 2DF | Westbrooke Development Ltd (site) Kladworx Ltd Lindfield Place 22 Lyndhurst Road Worthing, BN11 2DF | 2025-02-27 | 0.3333% | 1% | 0% | 0%
Commercial Road |  |  |  |  | E14 7NT | 605 Commercial Road London E14 7NT | 2025-03-31
[5 empty] | SE10 8LF | Kladworx Ltd 40 Greenwich High Road London SE10 8LF Alfie +44 (0) 7908 701 565

## Raw
Raw Materials Music | SO1398 | TBC | Fins, Angle & Stop Ends | On Hold | SW9 0DJ | Raw Material Music & Media Education 2 Robsart St SW9 0DJ | 2024-09-23 | 0% | 0% | 0% | 0%

## Eurowindows
The Whitestable School | SO1412 | 8021 | Pressings | In Production | SS17 0JJ | EuroWindows Ltd Poley Road Stanford-Le-Hope Essex, SS17 0JJ | 2024-09-30 | 2024-10-11 | 1.667% | 5% | 0% | 0%
Buckingham Palace | SO-1452 | 8182 | Additional Brackets | Ready to Dispatch | SS17 0JJ | EuroWindows Ltd Poley Road Stanford-Le-Hope Essex, SS17 0JJ | 2024-11-05 | 2024-11-11 | 83.33% | 100% | 100% | 50%

## FCS
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Stroudley Walk | SO1392 | 923 | Cill Pressings | In PPC |  | E3 3EW | McAleer & Rushe Contracts UK Ltd (For FCS Facades) Stroudley Walk E3 3EW | 2024-09-09 | 2024-09-23 | 66.67% | 100% | 100% | 0%
McCabe Court | SO1394 | 919 | Copings Gold Finish | In Production |  | E16 4HE | Vistry Group Plc (For FCS Facades) McCabe Court Barking Road E16 4HE | 2024-09-13 | 2024-09-23 | 33.33% | 100% | 0% | 0%
Wembley | SO1414 | 982 | Angle Pressing | In Production |  | HA9 0GB | FCS Facades McAleer & Rushe Contracts UK 10 Fulton Road, Wembley London, HA9 0GB | 2024-10-01 |  | 0.3333% | 1% | 0% | 0%
CSH Leeds | SO-1448 | 1055 | Angles | Ready to Dispatch |  | LS1 4HT | McAleer & Rushe Contracts UK Ltd City Square House 51 Aire Street Leeds LS1 4HT | 2024-10-30 | 2024-11-12 | 83.33% | 100% | 100% | 50%
McCabe Court | SO-1449 | 1061 | Butt Straps | Ready to Dispatch |  | E16 4HE | Vistry Group Plc (For FCS Facades) McCabe Court Barking Road E16 4HE | 2024-10-31 | 2024-11-11 | 83.33% | 100% | 100% | 50%
McCabe Court | SO-1451 | 1068 | Flashing & C-Profiles | Ready to Dispatch |  | E16 4HE | Vistry Group Plc (For FCS Facades) McCabe Court Barking Road E16 4HE | 2024-11-05 | 2024-11-11 | 83.33% | 100% | 100% | 50%
Camden Good Yard | [5 empty] | NW1 8EH | St George Plc Camden Goods Yard Chalk Farm Road, Chalk Farm Camden Town,London, NW1 8EH
Tunebridge Wells | [5 empty] | TN1 1PN | McAleer & Rushe Contracts UK Ltd (For FCS Facades) 1 Church Road Tunbridge wells TN1 1PN
Drury Lane | SO-1691 | 1662 | Window Surrounds & Flashings | In Production |  | WC2B 5PN | McAleer & Rushe Contracts UK Ltd (For FCS Facades) 161 Drury Lane London, WC2B 5PN Contact: Ruslan +44 (0) 7896 059 740 | 30/04/205 | 2025-05-27 | 0.3333% | 1% | 0% | 0%

## AJE
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Clarendon Road | SO1324 | DT157 | Windows Cills L2 & L3 | In production | Ready to dispatch | N8 0NW | AJE Facades Clarendon Road Block E1 & E3 C/O St William, Mary Neuner road Wood Green N8 0NW | 2024-07-18 | 2024-08-01 | 0.3333% | 1% | 0% | 0% | Pass to production | AJE Facades | Clarendon Road | Block E1 & E3 | C/O St William | Mary Neuner Road | Wood Green | N8 0NW
White City | SO1329 | CA2678 | C-Profiles | In production | XXX | W12 7RQ | White City 64 Wood Lane, Depod Road W12 7RH AJE Facades C/O St James | 2024-07-22 | 2024-08-01 | 0.3333% | 1% | 0% | 0% |  | White City | 64 Wood Lane | Depod Road | W12 7RH | AJE Facades
[6 empty] | HA9 0GB | Wembley NE01 FAO: AJE Facades (Gate 1) C/O McAleer & Rushe Fulton Road London, HA9 0GB
[6 empty] | N22 6TR | AJE Facades Clarendon Road Block E1 & E3 C/O St William, Silsoe Road Wood Green N22 6TR
[6 empty] | SW11 7DP | A01 Marketing Suite Embassy Gardens 29 Nie Elms Lane London, SW11 7DP
Project Reality | [5 empty] | WC2H 9FA | Project Reality C/O Bennett Construction Ltd Old Brewers Yard London WC2H 9FA Delivery gate on Shelton Street Cip +44 (0) 7738 899 112

## Rusgold
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Sutton Park House | SO1328 | PO1070 | Louvres Panels | In production | In production | SM1 4LD | RUSGOLD MANUFACTURING LTD Sutton Park House, 15 Carshalton Road SM1 4LD | 2024-07-22 | 2024-08-01 | 0.3333% | 1% | 0% | 0% | Painting/ none if mill finish
Bishop Avenue | SO1327 | PO1069 | Spandrel Panels and Flashings | In production | Pass to production | UB6 8UH | Rusgold Manufacturing LTD 426 Long Drive Greenford London UB6 8UH | 2024-07-19 | 2024-08-01 | 0.3333% | 1% | 0% | 0%

## MBP Facades
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Littlehampton | SO1393 | 56 | Cill Flashing Prod. 2 | In PPC |  | BN17 6FE | MPB Facades Ltd BokLok Bulding Site Littlehampton Fitzalan Road Littlehampton BN17 6FE | 2024-09-10 | 2024-09-23 | 100% | 100% | 100% | 100%
Fulbeck Avenue | SO-1468 | 34 |  |  |  | BN13 3RS | MPB Facades Ltd BokLok Building Site Fulbeck Avenue Worthing BN13 3RS
Rochester College | [5 empty] | ME1 1HB | Baxall Construction Limited Site Offices 213-217 High Street (ACCESS VIA BARDELL TERRACE / FURRELL'S ROAD Rochester Kent, ME1 1HB
Lockleaze | SO-1695 | 71 | Mock-Up | In production |  | BS7 9YG | MPB Facades Ltd BoKlok Housing Site Office Herkomer Close Lockleaze Bristol BS7 9YG | 2025-05-05 |  | 0.3333% | 1% | 0% | 0%

## QUBA
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Tunbridge Wells | SO-1430 | PO2068 | Linkbridge Perforated Panels | In production |  | TN4 9NT | FAO - Quba Construction Limited HG Site 36-40 St Johns Site Tunbridge Wells Kent, TN4 9NT | 2024-10-11 |  | 0.3333% | 1% | 0% | 0%
Briggit Leeds | [5 empty] | LS1 6BR | HG Construction Site 140 Briggate Street or Central Road Leeds, LS1 6BR
Brickdale House | [5 empty] | SG1 1AS | Brickdale House 21 Danestreet,Stevenage SG1 1AS

## EK Construction
Project | Project SO | Client PO | Materials | Status | Phase | Post Code | Delivery Adress | PO Date | Estimated Delivery Date | Current Update | Production | PPC | Dispatch
Maiden Lane | SO-1561 | SSM013 | Cabinet | In production |  | WC2E 7LJ | EK Construction Limited Sussex Mansions 36-39 Maiden Lane Covent Garden WC2E 7LJ | 2025-02-14 |  | 0.3333% | 1% | 0% | 0%
[6 empty] | SW1X 9HL | EK Construction Limited 8-12 William Street London SW1X 9HL Sebastian +44 (0) 7851 334 852